## Sheet1
SSW 567 Final Project Schedule | [14 empty] | Gantt Chart Template © 2012-2020 by Vertex42.com: Licensed for private use only. Do not publish on the internet.
Group 6: Neeti Mistry (Project Manager), Ahmad Shah (Test Planning), Sara Gaber (Performance Testing), Sohan Chatterjee (Unit Testing)
|  | GitHub Repo: | https://github.com/neetixmistry/SSW567-FinalProject
| Project Start Date: |  | 2024-11-11 |  | Display Week: |  | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
| Project Manager: |  | Neeti Mistry |  |  |  |  | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02
[8 empty] | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08
WBS | Task | Lead | Start | End | Days | % Done | Work Days | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Project Planning | Neeti Mistry | 2024-11-11 | 2024-11-22 | 12 | 100% | 10
1.1 | Define Project Scope | Neeti Mistry | 2024-11-11 | 2024-11-13 | 3 | 100% | 3
1.2 | Identify Key Milestones | Neeti Mistry | 2024-11-14 | 2024-11-16 | 3 | 100% | 2
1.3 | Resource Allocation | Neeti Mistry | 2024-11-17 | 2024-11-19 | 3 | 100% | 2
1.4 | Finalize Timeline | Neeti Mistry | 2024-11-20 | 2024-11-22 | 3 | 100% | 3
2 | Requirement Testing | Neeti Mistry | 2024-11-11 | 2024-11-14 | 4 | 100% | 4
2.1 | Identify Ambiguities in Requirements | Neeti Mistry | 2024-11-11 | 2024-11-12 | 2 | 100% | 2
2.2 | Clarify Ambiguities with Assumptions or Additional Info | Neeti Mistry | 2024-11-12 | 2024-11-13 | 2 | 100% | 2
2.3 | Rewrite Requirement Specifications | Neeti Mistry | 2024-11-13 | 2024-11-14 | 2 | 100% | 2
3 | Unit Testing | Sohan Chatterjee | 2024-11-14 | 2024-11-29 | 16 | 100% | 12
3.1 | Implement Functions for Requirement Specifications (MRTD.py) | Ahmad Shah | 2024-11-14 | 2024-11-26 | 13 | 100% | 9
3.2 | Write Test Cases for Each Function (MTTDtest.py) | Sohan Chatterjee & Sara Gaber | 2024-11-26 | 2024-11-27 | 2 | 100% | 2
3.3 | Generate Coverage Report and Ensure >80% Coverage | Sohan Chatterjee | 2024-11-26 | 2024-11-27 | 2 | 100% | 2
3.4 | Perform Mutation Testing Using MutPy | Sohan Chatterjee | 2024-11-28 | 2024-11-29 | 2 | 100% | 2
3.5 | Create Additional Test Cases (Bonus Point) | Sohan Chatterjee | 2024-11-29 | 2024-11-29 | 1 | 100% | 1
3.6 | Set Up GitHub Code Repository & Complete PDF Report | Neeti Mistry & Sohan Chatterjee | 2024-11-28 | 2024-11-29 | 2 | 100% | 2
4 | Performance Testing | Sara Gaber | 2024-11-27 | 2024-12-02 | 6 | 100% | 4
4.1 | Measure Execution Times for First 100 Records | Sara Gaber | 2024-11-27 | 2024-11-28 | 2 | 100% | 2
4.2 | Measure Execution Times for First 1000 Records | Sara Gaber | 2024-11-27 | 2024-11-30 | 4 | 100% | 3
4.3 | Measure Execution Times for First 10000 Records | Sara Gaber | 2024-11-27 | 2024-11-30 | 4 | 100% | 3
4.4 | Write Execution Times to CSV File | Sara Gaber | 2024-11-27 | 2024-11-30 | 4 | 100% | 3
4.5 | Generate Plot of Execution Times (CSV Data) | Neeti Mistry & Sara Gaber | 2024-11-29 | 2024-11-30 | 2 | 100% | 1
4.6 | Write 1-2 Paragraphs Explaining Results | Neeti Mistry & Sara Gaber | 2024-11-30 | 2024-12-02 | 3 | 100% | 1
5 | Test Planning | Ahmad Shah | 2024-12-02 | 2024-12-06 | 5 | 100% | 5
5.1 | Write Introduction Section of Test Plan | Neeti Mistry | 2024-12-02 | 2024-12-02 | 1 | 100% | 1
5.2 | Reference Relevant Document Section | Ahmad Shah | 2024-12-02 | 2024-12-02 | 1 | 100% | 1
5.3 | Testing Scope Section | Neeti Mistry | 2024-12-02 | 2024-12-03 | 2 | 100% | 2
5.4 | Testing Approach Section | Neeti Mistry | 2024-12-03 | 2024-12-05 | 3 | 100% | 3
5.5 | Schedule Section | Ahmad Shah | 2024-12-04 | 2024-12-05 | 2 | 100% | 2
5.6 | Approvals Section | Ahmad Shah | 2024-12-05 | 2024-12-05 | 1 | 100% | 1
5.7 | Review and Submit Test Plan | Neeti Mistry, Ahmad Shah, Sohan Chatterjee, & Sara Gaber | 2024-12-06 | 2024-12-06 | 1 | 100% | 1